## Top
Delivery Date | Task | Requirement Type | Total of Estimated Hrs | Total of Estimated Amount INR | Received Amount INR | Received On
24-Jan | Bill Vs Sales | New Requirements | 3 | 1800
| Bills Cut & Lines Cut | New Requirements | 2 | 1200
| Daily Stock Movement | New Requirements | 3 | 1800
| Item hagiarchy grouping and categories changes | New Requirements | 2 | 1200
| New Clients | New Requirements | 2 | 1200
| Order Vs Invoice | New Requirements | 3 | 1800
| Order vs Invoice vs Delivery | New Requirements | 4 | 2400
| Outstanding Ledger By Customer wise | New Requirements | 8 | 4800
| Outstanding Tracking Report By Customer | New Requirements | 4 | 2400
| Price List | New Requirements | 2 | 1200
| Van Loading Invoices | New Requirements | 2 | 1200
| Van Loading Items | New Requirements | 3 | 1800
25-Jan | WD Abstract With Gross Profit and Margin | Change Request | 1 | 600
26-Jan | Arc Item Master With Mapping Details | New Requirements | 0.5 | 300
28-Jan | Collection Report By Salesman, Date | New Requirements | 4 | 2400
29-Jan | Customer Aging Report | New Requirements | 1 | 600
30-Jan | Forum Support | Support | 0.5 | 200
31-Jan | PRINTING invoice history by timeline | New Requirements | 1 | 600
01-Feb | Add Salesman and Beat details in Van Loading Invoice Report | Support | 0.1 | 40
| Last sales Invoice Print & Count of printings on Print and Van Loading Invoice under Arc Reports -> Billing. | New Requirements | 2 | 1200
| Sales Amendment is not working in a node system and some of the customer menu is not available in the same node system. | Support | 0.2 | 80
| WD Abstract | New Requirements | 6 | 3600
03-Feb | Total Outstanding, No of bills by salesman and salesman Category like food, PCP, bingo | New Requirements | 6 | 3600
Grand Total |  |  | 60.3 | 36020 | 0
|  | Visit On | 2020-01-04 | 1000 | 1000 | 2020-01-14
|  | Visit On | 2020-01-11 | 1000 | 1000 | 2020-01-14
|  | Visit On | 2020-01-25 | 1000 | 0
|  | Visit On | 2020-02-01 | 1000 | 0
|  |  |  | 4000 | 2000
|  | Payment Pending |  | 38020
Billing Details
|  | Purpose | Charges
|  | New Requirements | 600
|  | Change Request | 600
|  | Support | 400
|  | Visit Cost / Day | 1000

## Tasks
ARC Sify Forum and Additional Requirements
No | Task | Remarks | Clarifications | Responsibility | Estimated Hrs | Requirement Type | Status | Working Progress % | Delivery Date
1 | Item hagiarchy grouping and categories changes | Each Item Should be grouped by Category Group Like GR1, GR2, GR3, GR4 and It should grouped by family like Foods, Cigrate, PCP and it have sub family with micro groups. All the reports should have these details. |  | Manickam.G | 2 | New Requirements | Completed | 100% | 2020-01-24
2 | Item Short Name Changes in Reports and Invoice Print | The Alternative Item Names should be maintained separately and that name should be used in Sales Invoice Print and Report Printings | In the given Item Name Master file some of the names are duplicated. That intimated. Waiting for final master. | Praveena / Mano / Vijay | 2 | New Requirements | In Progress | 80%
3 | Each User should have separate User Name Password. And each user should have separate responsibility |  | unique UserName password created for each users, Needs to set the Responsibility to each one. | Manickam.G | 1 | New Requirements | In Progress | 50%
4 | Item should be list based on FIFO in the sales invoice screen and Vajra | Due to old stocks and Expiry issues it needs to apply | The Expiry details are not available for each items and batches. It needs to capture. After that this will take care. | Manickam.G | 0 | New Requirements | Pending | 0%
5 | ARC Sales Bill Format | New Bill Print Format | Format Requirement Pending | Praveena / Mano / Vijay | 0 | New Requirements | Pending | 0%
6 | New Clients | Additional Sify Forum Clients for each and every system in ARC |  | Manickam.G | 2 | New Requirements | Completed | 100% | 2020-01-24
7 | Customer Master Manager | The Master should have additional informations like GPS details, Customer Zone, Sorting order in the Delivery belt and Order Belt, Billing and Shipping address and etc.. | Complete requirement needs to discuss | Praveena / Mano / Vijay | 0 | New Requirements | Pending | 0%
8 | CGST & Non CGST report | Based on the Customer classification like GST customer / Non GST Customer the Sales details should be splitted by date wise, month wise and year wise |  | Manickam.G | 0 | New Requirements | Pending | 0%
9 | Shop Closed Status | Needs to track the closed Shops |  | Manickam.G | 0 | New Requirements | Pending | 0%
10 | Vajra Item Management | Restrict Vajra Items based on the Salesman / Scheme Period / Fast Movings. The Items should be reordered based on the date and given classification | The Date based classification should be prepared and captured. Next This will take care. | Praveena / Mano / Vijay | 0 | New Requirements | Pending | 0%
11 | Bill Sequence | For the Order / Delivery purpose, the bill should be sequenced by some external support | The Customer sequence should be captured by Customer Master Manager and will take care of this | Praveena / Mano / Vijay | 0 | New Requirements | Pending | 0%
12 | Van Loading Items | Based on the Document Type mapping on the sales invoice the Van Loading report should be generate under ARC Reports. This report should have date and document type filter |  | Manickam.G | 3 | New Requirements | Completed | 100% | 2020-01-24
13 | Van Loading Invoices | Based on the Document Type mapping on the sales invoice the Van Loading report should be generate under ARC Reports. This report should have date, Payment Type and document type filter |  | Manickam.G | 2 | New Requirements | Completed | 100% | 2020-01-24
14 | Bill Vs Sales | The Report should have Each Document Type (Which has selected in sales invoice) the each item sales and delivery details and the different |  | Manickam.G | 3 | New Requirements | Completed | 100% | 2020-01-24
15 | Price List | This report should have current Price for each and every items with all available tax components and tax value |  | Manickam.G | 2 | New Requirements | Completed | 100% | 2020-01-24
16 | BillsCut & LinesCut | The Report should have each salesman Bill cut and line cut as per the date filter. |  | Manickam.G | 2 | New Requirements | Completed | 100% | 2020-01-24
17 | Order Vs Invoice | This report should have the Order vs Sales details |  | Manickam.G | 3 | New Requirements | Completed | 100% | 2020-01-24
18 | Order vs Invoice vs Delivery | This report should have the Order vs Sale Made and Actual Delivery details |  | Manickam.G | 4 | New Requirements | Completed | 100% | 2020-01-24
19 | Outstanding Tracking Report By Customer | This Report should have to track each customer each and every transaction by date with final outstanding |  | Manickam.G | 4 | New Requirements | Completed | 100% | 2020-01-24
20 | Outstanding Ledger By Customer wise | This Report have Actual Outstanding of the customer and On hand Cheque details with Each and every transaction details with break up. |  | Manickam.G | 8 | New Requirements | Completed | 100% | 2020-01-24
21 | Daily Stock Movement | The Report have each and every batch stock movement like purchase, sales, sales return to cross verify |  | Manickam.G | 3 | New Requirements | Completed | 100% | 2020-01-24
22 | WD Abstract | The Abstract report should have each month wise Opening stock and value, Over all month purchase value with tax and without tax, Over all month sales value with tax and without tax, Over all month sales return value with tax and without tax, and month end closing stock and value. Based on month selection this should generated. | The Abstract should be conside the actual sales without other service sales. | Manickam.G | 6 | New Requirements | Completed | 100% | 2020-02-01
23 | No Stock Items as per the priority Items for Next day process | This Report should have Zero stock or Non minimum stock (as per item Norm) for the Priority items | Needs to Set orm and Priority items | Praveena / Mano / Vijay |  | New Requirements | Pending | 0%
24 | Stock Aging Report | This Report should use to maintain the Stocks AS per FIFO / LIFO logic | Once Capture Item Expiry Details this should be take care | Manickam.G |  | New Requirements | Pending | 0%
25 | Category Group Wise Sales Report for Claim |  | Need Report Format | Praveena / Mano / Vijay |  | New Requirements | Pending | 0%
26 | PRINTING invoice history by timeline | New Report for analysis how many prints taken for each invoice in the van by the date. |  | Manickam.G | 1 | New Requirements | Completed | 100% | 2020-01-31
27 | Ds wise SR value by date |  |  | Manickam.G |  | New Requirements | Pending | 0%
28 | Delivery tracking system for each invoice |  |  | Manickam.G |  | New Requirements | Pending | 0%
29 | Van loading based on shipping address |  | After complete Customer Master Manager and will take care of this | Manickam.G |  | New Requirements | Pending | 0%
30 | Over all Scheme spend by date wise by category group |  | Need Report Format | Praveena / Mano / Vijay |  | New Requirements | Pending | 0%
31 | Sale Return Product Batch / Sale Invoice Id Verification |  |  | Manickam.G |  | New Requirements | Pending | 0%
32 | Purchase Return Product Batch / Purchase Invoice Id Verification |  |  | Manickam.G |  | New Requirements | Pending | 0%
33 | Sale Return Product Batch correction / suggestion |  |  | Manickam.G |  | New Requirements | Pending | 0%
34 | WD Abstract With Gross Profit and Margin | The Report should have Include the Gross Profit (Actual Sales On PTS - Actual Sales on PTR) And The 1.45% margin value for Actual Sales with PTS and Diffrents betweeen GP and Margin Profit for each Group. |  | Manickam.G | 1 | Change Request | Completed | 100% | 2020-01-25
35 | Arc Item Master With Mapping Details | The Report should have all mapping details from ARC and it should show if the item name is duplicate |  | Manickam.G | 0.5 | New Requirements | Completed | 100% | 2020-01-26
36 | Collection Report By SalesMan, Date | The Report Should have to list all collection by salesman and from date, to date |  | Manickam.G | 4 | New Requirements | Completed | 100% | 2020-01-28
37 | Vehicle trip sheet tracking |  |  |  |  | New Requirements | Pending | 0% | 2020-01-26
38 | Order vs Sales By Van | This report should have to track all order vs Sales by customer and date range and van |  | Manickam.G | 2 | New Requirements | Pending | 100% | 2020-01-29
39 | Customer Aging Report | This Report should have to identified with how long the customer attached with us and what is the last transaction date with us and how long they still idle without any transactions. |  | Manickam.G | 1 | New Requirements | Completed | 100% | 2020-01-29
40 | Forum Support | Request for Remove Loyalty points and payment details from Sales Invoice Print. |  | Manickam.G | 0.5 | Support | Completed | 100% | 2020-01-30
41 | Last sales Invoice Print & Count of printings on Print and Van Loading Invoice under Arc Reports -> Billing. | Capture the Date and Update the count of times to print the invoice and will be add in to the report and the requested report. | The Details Captured while trigger print and the same added in to the requested report. Needs to add the print format. | Manickam.G | 2 | New Requirements | Completed | 100% | 2020-02-01
42 | Forum Support | Requested to Modify the old date collections for invalid Cheque entry |  | Manickam.G
43 | Order Vs Delivery Growth Factor Report / Chat
44 | Sales Amentment is not working in a node system and some of the customer menu is not available in the same node system. | It works in server and other node system. But not working in this System. |  | Manickam.G | 0.2 | Support | Completed | 100% | 2020-02-01
45 | Add SalesMan and Beat details in Van Loading Invoice Report |  |  | Manickam.G | 0.1 | Support | Completed | 100% | 2020-02-01
46 | Sales Return Damage customer wise date wise value |  |  | Manickam.G |  | New Requirements | Pending | 0%
47 | Total Outstanding, No of bills by salesman and salesman Category like food, PCP, bingo | 2 Reports, 1 for all outstanding and aging > 0 value and another one is cumilative value and not of bills for each category and salesma | 2 Reports provide 1. Current Outstanding 2. Current Outstanding Consolidation | Manickam.G | 6 | New Requirements | Completed | 100% | 2020-02-03
48 | Outstanding report by outstanding day wise like less than 30 days, more than 30 days in row wise. |  | Need Report Format in Excel with required parameters | Praveena |  | New Requirements | Pending | 0%
49 | Add Salesman and Beat filter in Outstanding ledger report